## Project Overview
Item # | Deliverable | Description | Status | Owner | Dependencies | Due Date | Notes
1 | Combinations Sheet | All 52 combinations (V+M+F) with system flags | IN PROGRESS | PM | None | Week 1 | Requires UW validation
2 | Flow Engine Definition | Input/Output parameters, layer rules | NOT STARTED | PM + Tech | Item 1 | Week 1 | Defines system architecture
3 | Flow Architecture | L0-L6 layers, construct-specific flows | NOT STARTED | PM + Design | Items 1, 2 | Week 1 | Visual flow documentation
4 | UI Components | Component specs, variants, states | IN PROGRESS | Design | Item 3 | Week 2 | Working with design system
5 | Content Framework | Copy for all layers, constructs, payment models | NOT STARTED | Content Designer | Items 1, 3, 4 | Week 2 | Coordinate with CD
6 | Testing Flows | Test matrix for all 52 combinations | NOT STARTED | QA + PM | Items 1-5 | Week 3 | Manual + automated

## 1. Combinations Sheet
Task | Description | Status | Notes
Define VANILLA combinations | Document all 21 Vanilla scenarios | DONE | V01-V21 defined
Define MODULAR combinations | Document all 11 Modular scenarios | DONE | M01-M11 defined
Define FLEX combinations | Document all 20 Flex scenarios | DONE | F01-F20 defined
Add System Flags | Min Participation, Pre-Enrollment, CD Check, Grade-Based | DONE | Added to all combos
Add E-Card Eligibility | Map e-card generation rules | DONE | Yes/Conditional/Pending
Add Real-World Examples | Describe each combo in business terms | DONE | Added examples
Validate with Underwriting | Confirm combinations match actual RFQs | PENDING | Schedule meeting
Remove theoretical-only combinations | Keep only real-world scenarios | PENDING | Post-UW validation

## 2. Flow Engine
Parameter Type | Parameter Name | Data Type | Source | Description | Used In
INPUT | constructType | Enum: vanilla¦modular¦flex | Backend Config | Policy construct type | All layers
INPUT | base.type | Enum: fixed¦swappable¦wallet | Backend Config | Base plan changeability | L1, L3
INPUT | base.paidBy | Enum: employer¦employee¦partial | Backend Config | Who pays for base | L5
INPUT | base.options[] | Array of PlanTier | Backend Config | Available base plans (Modular/Flex) | L3
INPUT | walletAmount | Number | Backend Config | Employer wallet amount (Flex) | L1, L3, L4, L5
INPUT | topUp.available | Boolean | Backend Config | Is top-up available | L4
INPUT | topUp.type | Enum: standard¦modular¦consolidated | Backend Config | Type of top-up | L4
INPUT | topUp.paidBy | Enum: employer¦employee | Backend Config | Who pays for top-up | L5
INPUT | topUp.options[] | Array of TopUpOption | Backend Config | Available top-up options | L4
INPUT | secondary.available | Boolean | Backend Config | Is secondary plan available | L4
INPUT | secondary.paidBy | Enum: employer¦employee | Backend Config | Who pays for secondary | L5
INPUT | secondary.familyDefinition | Enum: parents¦children¦custom | Backend Config | Who secondary covers | L4
INPUT | secondary.siOptions[] | Array of Number | Backend Config | SI options for secondary | L4
INPUT | addOns.available | Boolean | Backend Config | Are add-ons available | L4
INPUT | addOns.list[] | Array of AddOn | Backend Config | Available add-ons | L4
INPUT | addOns.paidBy | Enum: employer¦employee¦mixed | Backend Config | Who pays for add-ons | L5
INPUT | addOns.familyScope | Enum: base¦custom | Backend Config | Add-on family definition | L4
INPUT | flags.minParticipation | Boolean | Backend Config | Is min participation required | L6, Post
INPUT | flags.preEnrollment | Boolean | Backend Config | Is this pre-enrollment phase | L6
INPUT | flags.cdBalanceCheck | Boolean | Backend Config | Check CD balance before e-card | L6, Post
INPUT | flags.gradeBasedPlans | Boolean | Backend Config | Filter plans by grade | L3
INPUT | employee.grade | String | Backend Config | Employee grade/slab | L3
INPUT | employee.existingMembers[] | Array of Member | Backend/DB | Pre-filled family members | L2
OUTPUT | layersToShow[] | Array of LayerID | Flow Engine | Which layers to render | Navigation
OUTPUT | layerConfig[layerId] | Object | Flow Engine | What to show in each layer | Rendering
OUTPUT | decisionsRequired[] | Array of Decision | Flow Engine | What user must decide | Validation
OUTPUT | premiumBreakdown | Object | Premium Engine | Employer/Employee split | L5, L6
OUTPUT | walletUsage | Object | Premium Engine | Wallet spent/remaining (Flex) | L3, L4, L5
OUTPUT | validationRules[] | Array of Rule | Validation Engine | Family/plan validation rules | L2, L3
OUTPUT | eCardEligibility | Enum: instant¦pending¦blocked | Flow Engine | E-card generation status | L6, Post

## 3. Flow Architecture
Layer | Name | VANILLA | MODULAR | FLEX | Components | Exit Condition
L0 | Context & Welcome | SHOW | SHOW | SHOW | Welcome, Progress, Overview | Click Continue
L1 | Base Coverage View | SHOW | SHOW | SHOW | Coverage Card, Benefits, Wallet (Flex) | Click Continue
L2 | Family Configuration | SHOW if family editable | SHOW if family editable | SHOW (dynamic) | Member Cards, Add Form | Confirm family
L3 | Plan Selection | SKIP | SHOW | SHOW | Plan Selector, Comparison, Wallet Display | Select plan + Continue
L4 | Enhancement Options | SHOW if options exist | SHOW if options exist | SHOW if options exist | Top-up, Secondary, Add-ons | Make selections + Continue
L5 | Premium & Payment | SHOW if employee pays | SHOW if employee pays | SHOW if wallet overflow | Premium Calculator, Payment Info | Review + Continue
L6 | Review & Consent | SHOW | SHOW | SHOW | Summary, Consent, Submit | Consent + Submit

## 4. UI Components
Component | Priority | Design Status | Dev Status | Notes
Progress Stepper | P0 | NOT STARTED | NOT STARTED | Needed for all flows
Coverage Card | P0 | NOT STARTED | NOT STARTED | Core component
Plan Selector | P0 | NOT STARTED | NOT STARTED | Critical for Modular/Flex
Member Card | P0 | NOT STARTED | NOT STARTED | For L2
Member Form | P0 | NOT STARTED | NOT STARTED | Add/Edit family
Premium Calculator | P0 | NOT STARTED | NOT STARTED | Real-time premium display
Wallet Display | P0 (Flex) | NOT STARTED | NOT STARTED | Flex-specific
Consent Checkbox | P0 | NOT STARTED | NOT STARTED | For L6
Review Summary | P0 | NOT STARTED | NOT STARTED | For L6
Success Screen | P0 | NOT STARTED | NOT STARTED | Post-submission
Error Message | P0 | NOT STARTED | NOT STARTED | Error handling
Add-on Card | P1 | NOT STARTED | NOT STARTED | For L4
Top-up Card | P1 | NOT STARTED | NOT STARTED | For L4
Secondary Plan Card | P1 | NOT STARTED | NOT STARTED | For L4
Tooltip/Info | P1 | NOT STARTED | NOT STARTED | Help system
Loading State | P1 | NOT STARTED | NOT STARTED | UI feedback
Comparison Table | P1 | NOT STARTED | NOT STARTED | Plan comparison

## 5. Content Framework
Content Type | Layer | Construct | Payment Context | Status | Content Designer Notes
Headlines | L0 | ALL | ALL | NOT STARTED | Welcome message variants
Headlines | L1 | VANILLA | Employer-Paid | NOT STARTED | "Your coverage is ready"
Headlines | L1 | MODULAR | Employer-Paid | NOT STARTED | "Your coverage + upgrade options"
Headlines | L1 | FLEX | Wallet | NOT STARTED | "Your benefits wallet is ready"
Headlines | L3 | MODULAR | Employee Upgrade | NOT STARTED | "Upgrade your protection"
Headlines | L3 | FLEX | Wallet | NOT STARTED | "Build your coverage"
Headlines | L4 | ALL | Employee-Paid | NOT STARTED | "Enhance your coverage"
Headlines | L5 | ALL | Employee-Paid | NOT STARTED | "Your investment breakdown"
Headlines | L6 | ALL | ALL | NOT STARTED | "Review and confirm"
CTA Buttons | ALL | ALL | ALL | NOT STARTED | Primary/Secondary CTAs
Tooltip Definitions | ALL | ALL | ALL | NOT STARTED | Insurance jargon glossary
Error Messages | ALL | ALL | ALL | NOT STARTED | Validation error copy
Success Messages | L6 | ALL | ALL | NOT STARTED | Submission success variants
Anxiety Reducers | ALL | ALL | ALL | NOT STARTED | Reassurance microcopy
Wallet Copy | L1, L3, L4, L5 | FLEX | Wallet | NOT STARTED | Wallet-specific messaging
E-card Status | Post | ALL | ALL | NOT STARTED | Instant/Pending/Blocked messages

## 6. Testing Flows
Combo ID | Construct | Flow Test | Premium Test | Edge Cases | Content Review | E2E Test | Notes
V01 | VANILLA | ☐ | ☐ | ☐ | ☐ | ☐
V02 | VANILLA | ☐ | ☐ | ☐ | ☐ | ☐
V03 | VANILLA | ☐ | ☐ | ☐ | ☐ | ☐
V04 | VANILLA | ☐ | ☐ | ☐ | ☐ | ☐
V05 | VANILLA | ☐ | ☐ | ☐ | ☐ | ☐
V06 | VANILLA | ☐ | ☐ | ☐ | ☐ | ☐
V07 | VANILLA | ☐ | ☐ | ☐ | ☐ | ☐
V08 | VANILLA | ☐ | ☐ | ☐ | ☐ | ☐
V09 | VANILLA | ☐ | ☐ | ☐ | ☐ | ☐
V10 | VANILLA | ☐ | ☐ | ☐ | ☐ | ☐
V11 | VANILLA | ☐ | ☐ | ☐ | ☐ | ☐
V12 | VANILLA | ☐ | ☐ | ☐ | ☐ | ☐
V13 | VANILLA | ☐ | ☐ | ☐ | ☐ | ☐
V14 | VANILLA | ☐ | ☐ | ☐ | ☐ | ☐
V15 | VANILLA | ☐ | ☐ | ☐ | ☐ | ☐
V16 | VANILLA | ☐ | ☐ | ☐ | ☐ | ☐
V17 | VANILLA | ☐ | ☐ | ☐ | ☐ | ☐
V18 | VANILLA | ☐ | ☐ | ☐ | ☐ | ☐
V19 | VANILLA | ☐ | ☐ | ☐ | ☐ | ☐
V20 | VANILLA | ☐ | ☐ | ☐ | ☐ | ☐
V21 | VANILLA | ☐ | ☐ | ☐ | ☐ | ☐
M01 | MODULAR | ☐ | ☐ | ☐ | ☐ | ☐
M02 | MODULAR | ☐ | ☐ | ☐ | ☐ | ☐
M03 | MODULAR | ☐ | ☐ | ☐ | ☐ | ☐
M04 | MODULAR | ☐ | ☐ | ☐ | ☐ | ☐
M05 | MODULAR | ☐ | ☐ | ☐ | ☐ | ☐
M06 | MODULAR | ☐ | ☐ | ☐ | ☐ | ☐
M07 | MODULAR | ☐ | ☐ | ☐ | ☐ | ☐
M08 | MODULAR | ☐ | ☐ | ☐ | ☐ | ☐
M09 | MODULAR | ☐ | ☐ | ☐ | ☐ | ☐
M10 | MODULAR | ☐ | ☐ | ☐ | ☐ | ☐
M11 | MODULAR | ☐ | ☐ | ☐ | ☐ | ☐
F01 | FLEX | ☐ | ☐ | ☐ | ☐ | ☐
F02 | FLEX | ☐ | ☐ | ☐ | ☐ | ☐
F03 | FLEX | ☐ | ☐ | ☐ | ☐ | ☐
F04 | FLEX | ☐ | ☐ | ☐ | ☐ | ☐
F05 | FLEX | ☐ | ☐ | ☐ | ☐ | ☐
F06 | FLEX | ☐ | ☐ | ☐ | ☐ | ☐
F07 | FLEX | ☐ | ☐ | ☐ | ☐ | ☐
F08 | FLEX | ☐ | ☐ | ☐ | ☐ | ☐
F09 | FLEX | ☐ | ☐ | ☐ | ☐ | ☐
F10 | FLEX | ☐ | ☐ | ☐ | ☐ | ☐
F11 | FLEX | ☐ | ☐ | ☐ | ☐ | ☐
F12 | FLEX | ☐ | ☐ | ☐ | ☐ | ☐
F13 | FLEX | ☐ | ☐ | ☐ | ☐ | ☐
F14 | FLEX | ☐ | ☐ | ☐ | ☐ | ☐
F15 | FLEX | ☐ | ☐ | ☐ | ☐ | ☐
F16 | FLEX | ☐ | ☐ | ☐ | ☐ | ☐
F17 | FLEX | ☐ | ☐ | ☐ | ☐ | ☐
F18 | FLEX | ☐ | ☐ | ☐ | ☐ | ☐
F19 | FLEX | ☐ | ☐ | ☐ | ☐ | ☐
F20 | FLEX | ☐ | ☐ | ☐ | ☐ | ☐